Gnome Foundation Proposal

July 19, 2000

LinuxWorld Conference & Expo

San Jose Convention Center

San Jose

August 14-17, 2000

OBJECTIVES

- Advance the free software/open source agenda as a central force in computing.

- Introduce The GNOME Foundation as the non-profit organization for advancing GNOME as the world’s leading free and easy-to-use desktop environment for the user.

- Demonstrate momentum/credibility for this foundation with announcements of support by leading vendors.

- Establish key executives from The GNOME Foundation and the vendor organizations as resources to reporters/analysts.

STRATEGY

To reinforce GNOME’s position as a leader in the open source movement, positioning GNOME as a unifying industry force across multiple vendors.

KEY MESSAGES

- The GNOME Foundation has been formed to formalize a group of individuals, from varying organizations and companies, who will be responsible for advancing GNOME.

- The GNOME desktop is the world’s leading free and easy-to-use desktop enviroment for the user; GNOME has been designed to run on all modern strains of Unix-like operating systems.

- The support of leading vendors, including Sun Microsystems, Eazel, Collab.Net, Helix Code, Red Hat, [others to come] demonstrates that the industry is coalescing behind GNOME as the desktop environment of the future.

ANNOUNCEMENT VEHICLE

In light of the number of speakers involved, the proposed vehicle for the announcement is a press conference on August 15th at LinuxWorld.

The press release should cross the wire that morning.  The more vendors involved and the bigger the names, the better the attendance.  The novelty of competing vendors (e.g. Sun, IBM, HP) aligning to support The Foundation will enhance the draw.  If major vendors do not commit, the interest level will drop accordingly.

We are in the process of determining what has been done already in terms of booking a conference facility for the event, either at the Convention Center or at the Fairmont.  We also need to determine, from show management, what events may be competing with this one.

Notable Aug. 15 events from the web site include:

Keynote, 10-11 a.m., Michael Dell

Immediately following, IDG/Torvalds Community Award Presentation

2:30-3:30 p.m. - Linux Geek Bowl, with many Linux gurus

5:30-6:30 p.m. - Exec. Roundtable with CEO of 6 Linux firms

We should plan for a session that lasts no more than an hour.  This would include approximately 45 minutes of presentations with a 15 minute Q&A.

Miguel de Icaza has been identified as the initial speaker.  Miguel will kick off the presentations and briefly describe the news being announced - the formation of the foundation and why it’s important.  When we have determined precisely how many speakers we’ll have, we can prepare a time budget for each speaker.  However, with multiple speakers, we can assume that their remarks should last just 5-10 minutes, as we’ll want to allow plenty of time for Q&A.

We’ll set up the room with a talk show format, using a podium with a series of chairs for other speakers.

Press Kit and Related Deliverables

- Agenda for event (CHEN)

- Press release announcing formation of Foundation (Eazel to own; but each vendor liaison will be responsible for content/legal approvals at their respective firms)

- Media advisory week before show to drive press/analyst attendance (CHEN who/what/when/where format - summarize from press release)

- Supporting vendor press releases (prepared and supplied by each vendor)

- List of vendors involved with relevant URLs, contact information (CHEN to coordinate)

- One page backgrounder on GNOME (to be determined)

- Q&A for internal use only (to be determined)

- Presentations - If speakers elect to use slides, they are responsible for developing their own slide presentations.  We’ll have standard AV equipment there, but assume we’ll keep it simple and that presentations will be run off laptops.

- Screenshots/photos - any graphics, in case requested.

- References: customers or analysts/open source gurus

Spokespeople

[Please provide names and titles.]

- Miguel de Icaza, founder of Helix Code

- Name, Collab.Net

- Name, Eazel

- Name, Red Hat

- Name, Sun Microsystems

- Name, IBM

- Name, H-P

- [others]

PRESS/ANALYST INVITES

CHEN will serve as the central point for inviting reporters and analysts.  We’ll ask for all parties to submit their press/analyst invite lists so that we can consolidate the lists.

We may also want to consider briefing 3-5 analysts in advance of the event.

In summary, CHEN will:

Develop email invitation

Consolidate press/analyst list

Send emails and follow-up emails/follow-up calls

Send advisory

Provide regular status updates on event attendance

Confirm with all attendees week before show

Timeline

**Week of June 17

Conducted kick off conference call

CHEN submits proposal to Sun for OK

CHEN submits proposal to announcement team

CHEN fine tunes proposal based on feedback/contributions

CHEN determines status of conference event location

CHEN checks with show management on other scheduled events

CHEN requests press list from show management

CHEN requests invite lists from all parties to build consolidated list for invites (will share this list with all parties)

Gnome team finalizes corporate participants

**Week of June 24

Next conference call slated for July 24, 1 p.m PT - Discuss open issues

Eazel prepares draft press release; other vendors provide input

CHEN builds consolidated press/analyst invite list, monitoring for updates to show registration list

CHEN starts to email/call/register reporters

CHEN coordinates with hotel or convention center on AV, food, logistics

CHEN drafts list of participating companies and contacts

**Week of July 31

CHEN continues to pursue/register reporters

Eazel revises press release

CHEN develops media advisory/submits for review/finalizes

CHEN schedules one-on-ones, if desired

CHEN sets up advance briefings with small group of analyts, if desired

**Week of August 7

CHEN continues to pursue/register reportersEazel finalizes press release early in week

CHEN issues media advisory on Aug. 7

Conference call rehearsal with all spokespersons on August 9

**Week of August 14

Rehearsal Monday evening

Speakers can revised as needed

Make any final press calls to confirm attendance

Attend/monitor event

Open Issues

- One-on-ones – On our next call, we should discuss whether we’d like to offer a short list of reporters one-on-one time after the main event.

- We need to project number of attendees.

- We need to discuss the agenda.

- Webcast of event?

- Ownership of Q&A?

- Prebrief select group of analysts?

- If Sun/HP/IBM are all involved, pitch to one daily in advance?  Status of their involvement?

# # #